## Screens
Screen name | Screen type | Main table | Description | Hours
Student course assignments | list | courseassignment | List all assignments for a scheduled course and user
Admin courses - completed | list | courseschedule | List all completed scheduled courses
Admin courses - current | list | courseschedule | List all current scheduled courses
Admin courses - future | list | courseschedule | List all future scheduled courses
My courses - current | list | courseschedule | List all current scheduled courses for user
My courses - completed | list | courseschedule | List all completed scheduled courses for user
My courses - future | list | courseschedule | List all future scheduled courses for user
Teaching - completed | list | courseschedule | List all completed teaching assignments for user
Teaching - current | list | courseschedule | List all current teaching assignments for user
Teaching - future | list | courseschedule | List all future teaching assignments for user
Roster | list | coursestudent | List all students for a scheduled course
Terms create | detail | lookupterm | Create a term
Terms delete | detail | lookupterm | Delete a term
Terms update | detail | lookupterm | Update a term
Terms list | list | lookupterm | List all terms
User create | detail | User | Create a user
User Update | detail | User | Update a user
Course assignment create | detail | courseassignment | Create a course assignment
course assignment delete | detail | courseassignment | Delete a course assignment
Course assignment update | detail | courseassignment | Update a course assignment
Course assignments | list | courseassignment | List all assignments for a scheduled course
Course schedule create | detail | courseschedule | Schedule a course
Course schedule delete | detail | courseschedule | Delete a scheduled course
Course schedule update | detail | courseschedule | Update a scheduled course
Course student grade | detail | coursestudent | Update/View a student's scheduled course grade
Courses create | detail | lookupcourse | Create a course
Courses delete | detail | lookupcourse | Delete a course
Courses update | detail | lookupcourse | Update a course
Courses list | list | lookupcourse | List all courses
Student assignment + submission + grade | detail | studentsubmission | Grade a student's submission for a course assignment
Student submission | detail | studentsubmission | Upload a file for a given scheduled course/assignment/user
Admin dashboard | Menu |  | Menu for admin functions

## Sprint 1
Teacher's Pet
Sprint #1 Tracking
Sprint #: |  | 1
Start date: |  | 2021-01-20
Total Team Members: |  | 4
Units allocated: |  | 34
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Wednesday | 2 Thursday | 3 Friday | 4 Saturday | 5 Sunday | 6 Monday | 7 Tuesday | 8 Wednesday | 9 Thursday | 10 Friday | 11 Saturday | 12 Sunday | 13 Monday | 14 Tuesday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | Actual
1 | 8 | Design | Screen mockups for account management module | Sally | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 4
2 | 2 | Design | Logical Data Model for the system | Sally | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
3 | 8 | Design | Activity Diagram for account management module | Sally | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
4 | 8 | Design | Requirements | Michael | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
5 | 1 | Design | Design application logo | Steve | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2
6 |  | Learn | Sign into Github | Team | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0.5 | 2.5
7 |  | Learn | Learn LucidChart | Michael, Steve, Joe | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 1 | 4.5
8 |  | Learn | Learn Django - first two tutorial modules | Team | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 6.5 | 8.5
9 |  | Learn | Learn Trello | Michael, Steve, Joe | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0.5 | 1 | 2.5
|  |  |  | Remaining units (actual) | 64 | 64 | 64 | 64 | 64 | 60 | 60 | 60 | 57 | 57 | 57 | 55 | 50 | 44 | 35
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 34
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Sally | Screen mockups for account management module | 2021-01-24 | bar: week 1 1
|  |  | Sally | Screen mockups for account management module | 2021-01-30 | bar: week 1 1
|  |  | Sally | Screen mockups for account management module | 2021-01-31 | bar: week 1 1
|  |  | Sally | Logical Data Model for the system | 2021-01-24 | bar: week 1 1
|  |  | Sally | Screen mockups for account management module | 2021-01-31 | bar: week 1 1
|  |  | Sally | Activity Diagram for account management module | 2021-01-31 | week 1 1: 2
|  |  | Michael | Requirements | 2021-01-24 | week 1 1: 2
|  |  | Steve | Design application logo | 2021-01-30 | bar: week 1 1
|  |  | Steve | Design application logo | 2021-02-01 | bar: week 1 1
|  |  | Sally | Sign into Github | 2021-01-27 | week 1 1: 0.5
|  |  | Joe | Sign into Github | 2021-01-27 | week 1 1: 0.5
|  |  | Sally | Learn Django - first two tutorial modules | 2021-01-27 | bar: week 1 1
|  |  | Michael | Sign into Github | 2021-02-02 | week 1 1: 0.5
|  |  | Michael | Learn Trello | 2021-02-02 | bar: week 1 1
|  |  | Steve | Sign into Github | 2021-01-31 | bar: week 1 1
|  |  | Steve | Learn Trello | 2021-02-01 | week 1 1: 0.5
|  |  | Steve | Learn Django - first two tutorial modules | 2021-02-02 | week 1 1: 2
|  |  | Steve | Learn Django - first two tutorial modules | 2021-02-01 | bar: week 1 1
|  |  | Steve | Learn LucidChart | 2021-02-01 | week 1 1: 0.5
|  |  | Michael | Learn LucidChart | 2021-02-02 | bar: week 1 1
|  |  | Michael | Learn Django - first two tutorial modules | 2021-02-02 | week 1 1: 2
|  |  | Joe | Learn Django - first two tutorial modules | 2021-02-02 | week 1 1: 2.5
|  |  | Joe | Learn LucidChart | 2021-02-01 | week 1 1: 3
|  |  | Joe | Learn Trello | 2021-01-27 | bar: week 1 1

## Sprint 2
Teacher's Pet
Sprint #2 Tracking
Sprint #: |  | 2
Start date: |  | 2021-02-03
Total Team Members: |  | 4
Units allocated: |  | 58
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[6 empty] | 1 Wednesday | 2 Thursday | 3 Friday | 4 Saturday | 5 Sunday | 6 Monday | 7 Tuesday | 8 Wednesday | 9 Thursday | 10 Friday | 11 Saturday | 12 Sunday | 13 Monday | 14 Tuesday | 15 Wednesday | 16 Thursday | 17 Friday | 18 Saturday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-12 | 2021-02-13 | 2021-02-14 | 2021-02-15 | 2021-02-16 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-20 | Actual
10 | 5 | Design | Requirements for academic perf mgt | Sally | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
11 | 5 | Design | Wireframes for academic perf mgt | Joe | 8 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9
12 | 5 | Design | Activity diagrams for academic perf mgt | Steve | 8 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
13 | 5 | Design | Use cases for academic perf mgt (removed 2/17/21) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | Design | Visual Asset creation | Steve | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
15 |  | Learn | Learn Gitlab | Team | 8 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
16 |  | Learn | Research software assurance and data protection | Joe | 8 | 1.5 | 1 | 4 | 0 | 0 | 0 | 0 | 4 | 1.5 | 1.5 | 1 | 0 | 0 | 0 | 0 | 2 | 0.5 | 4.5 | 21.5
17 |  | Learn | Learn Django - tutorial modules 3 through 7 | Team | 12 | 0 | 0 | 0.5 | 3.5 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 2.5 | 1 | 4 | 0 | 0 | 17.5
38 |  | Design | Requirements for all modules (added 2/17/21) | Sally | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
|  |  |  | Remaining units (actual) | 64 | 61.5 | 60.5 | 55 | 51.5 | 44.5 | 43.5 | 40.5 | 30.5 | 29 | 27.5 | 26.5 | 23.5 | 21.5 | 19 | 18 | 12 | 11.5 | 3
|  |  |  | Remaining units (ideal) |  | 60.4444 | 56.8889 | 53.3333 | 49.7778 | 46.2222 | 42.6667 | 39.1111 | 35.5556 | 32 | 28.4444 | 24.8889 | 21.3333 | 17.7778 | 14.2222 | 10.6667 | 7.1111 | 3.5556 | -1.954e-14
[11 empty] | 0 | 58
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Joe | Learn Gitlab | 2021-02-03 | bar: week 1 1
|  |  | Joe | Research software assurance and data protection | 2021-02-03 | week 1 1: 1.5
|  |  | Joe | Research software assurance and data protection | 2021-02-04 | bar: week 1 1
|  |  | Joe | Research software assurance and data protection | 2021-02-05 | week 1 1: 4
|  |  | Steve | Learn Gitlab | 2021-02-05 | bar: week 1 1
|  |  | Steve | Learn Django - tutorial modules 3 through 7 | 2021-02-05 | week 1 1: 0.5
|  |  | Joe | Learn Django - tutorial modules 3 through 7 | 2021-02-06 | bar: week 1 1
|  |  | Michael | Learn Django - tutorial modules 3 through 7 | 2021-02-06 | week 1 1: 2
|  |  | Steve | Learn Django - tutorial modules 3 through 7 | 2021-02-06 | week 1 1: 0.5
|  |  | joe | Wireframes for academic perf mgt | 2021-02-07 | week 1 1: 2
|  |  | Michael | Learn Gitlab | 2021-02-07 | bar: week 1 1
|  |  | Sally | Learn Gitlab | 2021-02-07 | bar: week 1 1
|  |  | Sally | Learn Django - tutorial modules 3 through 7 | 2021-02-07 | week 1 1: 2
|  |  | Steve | Activity diagrams for academic perf mgt | 2021-02-07 | bar: week 1 1
|  |  | Steve | Use cases for academic perf mgt | 2021-02-08 | week 1 1: 2
|  |  | Steve | Visual Asset creation | 2021-02-08 | bar: week 1 1
|  |  | Michael | Learn Django - tutorial modules 3 through 7 | 2021-02-09 | bar: week 1 1
|  |  | Steve | Visual Asset creation | 2021-02-09 | week 1 1: 2
|  |  | joe | Research software assurance and data protection | 2021-02-10 | week 1 1: 3
|  |  | Joe | Wireframes for academic perf mgt | 2021-02-10 | week 1 1: 6
|  |  | Joe | Research software assurance and data protection | 2021-02-10 | bar: week 1 1
|  |  | Joe | Research software assurance and data protection | 2021-02-11 | week 1 1: 1.5
|  |  | Joe | Research software assurance and data protection | 2021-02-12 | week 1 1: 1.5
|  |  | Joe | Research software assurance and data protection | 2021-02-13 | bar: week 1 1
|  |  | Joe | Learn Django - tutorial modules 3 through 7 | 2021-02-14 | week 1 1: 2
|  |  | Sally | Requirements for academic perf mgt | 2021-02-14 | bar: week 1 1
|  |  | joe | Learn Django - tutorial modules 3 through 7 | 2021-02-15 | bar: week 1 1
|  |  | Steve | Activity diagrams for academic perf mgt | 2021-02-15 | bar: week 1 1
|  |  | sally | Requirements for all modules (added 2/17/21) | 2021-02-20 | week 1 1: 3
|  |  | Michael | Learn Django - tutorial modules 3 through 7 | 2021-02-18 | week 1 1: 4
|  |  | Michael | Learn Django - tutorial modules 3 through 7 | 2021-02-16 | week 1 1: 2
|  |  | joe | Research software assurance and data protection | 2021-02-20 | week 1 1: 4.5
|  |  | joe | Learn Django - tutorial modules 3 through 7 | 2021-02-16 | week 1 1: 0.5
|  |  | joe | Learn Django - tutorial modules 3 through 7 | 2021-02-17 | bar: week 1 1
|  |  | joe | Research software assurance and data protection | 2021-02-18 | week 1 1: 2
|  |  | joe | Research software assurance and data protection | 2021-02-19 | week 1 1: 0.5
|  |  | Steve | Wireframes for academic perf mgt | 2021-02-21 | week 1 1: 2
|  |  | Steve | Wireframes for academic perf mgt | 2021-02-20 | bar: week 1 1

## Sprint 3
Teacher's Pet
Sprint #3 Tracking
Sprint #: |  | 3
Start date: |  | 2021-02-21
Total Team Members: |  | 4
Units allocated: |  | 63
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Sunday | 2 Monday | 3 Tuesday | 4 Wednesday | 5 Thursday | 6 Friday | 7 Saturday | 8 Sunday | 9 Monday | 10 Tuesday | 11 Wednesday | 12 Thursday | 13 Friday | 14 Saturday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-02-21 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-02-27 | 2021-02-28 | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | Actual
20 | 401 | Build | Build the main portal user interface - this will serve as the template for all user interfaces | Joe | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 400 | Build | Build the login system/user interface | Michael | 10 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
22 | 2 | Build | Build the database | Sally | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
23 | 2 | Design | Research connecting to the database in Django | Sally | 6 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16
24 |  | Design | Wireframes for remaining user interfaces | Steve | 20 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 2 | 0 | 0 | 5.5
25 |  | Build | Set up Git Branch for user interfaces | Joe | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 1
26 | 1 | Design | Visual assets - buttons, background colors, foreground colors, images | Steve | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
27 | 208-223 | Build | Classes user interfaces - maybe week 2 | not assigned | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining units (actual) | 64 | 64 | 61 | 60 | 53 | 49 | 49 | 44 | 43 | 43 | 42.5 | 41.5 | 38.5 | 38.5 | 30.5
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 63
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | sally | Build the database | 2021-02-22 | week 1 1: 3
|  |  | Sally | Research connecting to the database in Django | 2021-02-25 | week 1 1: 4
|  |  | Sally | Research connecting to the database in Django | 2021-02-27 | week 1 1: 4
|  |  | Michael | Build the login system/user interface | 2021-02-24 | week 1 1: 7
|  |  | Steve | Wireframes for remaining user interfaces | 2021-02-27 | bar: week 1 1
|  |  | Steve | Wireframes for remaining user interfaces | 2021-02-28 | bar: week 1 1
|  |  | Steve | Set up Git Branch for user interfaces | 2021-02-23 | week 1 1: 0.5
|  |  | Joe | computer was down for majority of the first part of sprint
|  |  | Steve | Wireframes for remaining user interfaces | 2021-02-23 | week 1 1: 0.5
|  |  | Steve | Wireframes for remaining user interfaces | 2021-03-03 | bar: week 1 1
|  |  | Steve | Wireframes for remaining user interfaces | 2021-03-04 | week 1 1: 2
|  |  | Steve | Visual assets - buttons, background colors, foreground colors, images | 2021-03-04 | bar: week 1 1
|  |  | Steve | Set up Git Branch for user interfaces | 2021-03-02 | week 1 1: 0.5
|  |  | Sally | Research connecting to the database in Django | 2021-03-06 | week 1 1: 8

## Sprint 4
Teacher's Pet
Sprint #4 Tracking
Sprint #: |  | 4
Start date: |  | 2021-03-07
Total Team Members: |  | 4
Units allocated: |  | 68
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Sunday | 2 Monday | 3 Tuesday | 4 Wednesday | 5 Thursday | 6 Friday | 7 Saturday | 8 Sunday | 9 Monday | 10 Tuesday | 11 Wednesday | 12 Thursday | 13 Friday | 14 Saturday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | Actual
20 | 401 | Build | Build the main portal user interface | Joe | 8 | 0.5 | 1.5 | 2 | 0 | 2.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5
31 | 1 | Design | Visual assets for main portal | Steve | 3 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
32 | 200-202 | Build | Classes UI 1.1 - Admin | Michael | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 203 | build | Classes UI 1.1 - Teacher | TBD | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 217 | build | Classes UI 1.1 - Student | TBD | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
35 | 2 | build | Integrate database and login system | Sally | 8 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7
36 |  | Learn | Research how to restore previous commits in Git | TBD | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 1 | design | Design wireframes for academics | Steve | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
39 |  | Learn | Back to basics with Django |  | 8
38 | 1 | design | Design wireframes for user info | Steve | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
|  |  |  | Remaining units (actual) | 64 | 63.5 | 62 | 60 | 60 | 49.5 | 48 | 45 | 44 | 44 | 44 | 44 | 44 | 44 | 40
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 68
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Joe | Build the main portal user interface | 2021-03-07 | week 1 1: 0.5
|  |  | Joe | Build the main portal user interface | 2021-03-08 | week 1 1: 1.5
|  |  | Joe | Build the main portal user interface | 2021-03-09 | week 1 1: 2
|  |  | Steve | Visual assets for main portal | 2021-03-12 | week 1 1: 0.5
|  |  | Steve | Build the main portal user interface | 2021-03-12 | week 1 1: 0.5
|  |  | Steve | Design wireframes for academics | 2021-03-14 | bar: week 1 1
|  |  | Michael | Classes UI 1.1 - Student | 2021-03-11 | week 1 1: 3
|  |  | Michael | Classes UI 1.1 - Student | 2021-03-13 | week 1 1: 2
|  |  | Sally | Integrate database and login system | 2021-03-11 | week 1 1: 2
|  |  | Sally | Integrate database and login system | 2021-03-11 | week 1 1: 3
|  |  | Joe | Build the main portal user interface | 2021-03-11 | week 1 1: 2.5
|  |  | Joe | Build the main portal user interface | 2021-03-12 | week 1 1: 0.5
|  |  | Joe | Build the main portal user interface | 2021-03-13 | bar: week 1 1
|  |  | Sally | Integrate database and login system | 2021-03-20 | week 1 1: 2
|  |  | Sally | Back to basics with Django | 2021-03-20 | week 1 1: 3
|  |  | Sally | Back to basics with Django | 2021-03-21 | week 1 1: 3
|  |  | Steve | Design wireframes for user info | 2021-03-20 | week 1 1: 2
|  |  | Steve | Back to basics with Django | 2021-03-15 | week 1 1: 2
|  |  | Joe | Back to basics with Django | 2021-03-17 | week 1 1: 2
|  |  | Joe | Back to basics with Django | 2021-03-18 | week 1 1: 2
|  |  | Joe | Back to basics with Django | 2021-03-20 | week 1 1: 0.5
|  |  | Joe | Back to basics with Django | 2021-03-21 | week 1 1: 0.5

## Sprint 5
Teacher's Pet
Sprint #5 Tracking
Sprint #: |  | 5
Start date: |  | 2021-03-30
Total Team Members: |  | 4
Units allocated: |  | 66
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Tuesday | 2 Wednesday | 3 Thursday | 4 Friday | 5 Saturday | 6 Sunday | 7 Monday | 8 Tuesday | 9 Wednesday | 10 Thursday | 11 Friday | 12 Saturday | 13 Sunday | 14 Monday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | Actual
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | build | Classes UI 1.4 Future Classes | Joe | 8 | 0 | 0.5 | 1.5 | 0 | 0.5 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6.5
32 | 200-202 | Build | Classes UI 1.1 Current Classes | Michael | 8 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
33 | 203 | Build | Classes UI 1.3 Completed Classes | Michael | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Build | Classes UI 1.2 Class Details | Sally | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1.5 | 0.5 | 5
35 | 2 | build | Integrate database and UIs | Sally | 16 | 0 | 0 | 0 | 3 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 17
|  | build | Classes UI 1.2. Roster Details | Steve | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 1 | 0 | 1 | 8
37 | 1 | design | Design wireframes for academics | Steve | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining units (actual) | 64 | 64 | 63.5 | 57 | 54 | 47.5 | 43.5 | 41.5 | 40.5 | 39.5 | 34.5 | 31.5 | 28.5 | 27 | 22.5
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 66
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Michael | Classes UI 1.1 Current Classes | 2021-04-01 | week 1 1: 5
|  |  | Joe | Classes UI 1.4 Future Classes | 2021-03-31 | week 1 1: 0.5
|  |  | Joe | Classes UI 1.4 Future Classes | 2021-04-01 | week 1 1: 1.5
|  |  | Joe | Classes UI 1.4 Future Classes | 2021-04-03 | week 1 1: 0.5
|  |  | Joe | Classes UI 1.4 Future Classes | 2021-04-05 | week 1 1: 2
|  |  | Joe | Classes UI 1.4 Future Classes | 2021-04-06 | bar: week 1 1
|  |  | Joe | Classes UI 1.4 Future Classes | 2021-04-07 | bar: week 1 1
|  |  | Sally | Integrate database and UIs | 2021-04-02 | week 1 1: 3
|  |  | Sally | Integrate database and UIs | 2021-04-03 | week 1 1: 6
|  |  | Sally | Integrate database and UIs | 2021-04-04 | week 1 1: 4
|  |  | Sally | Integrate database and UIs | 2021-04-10 | week 1 1: 4
|  |  | Sally | Integrate database and UIs | 2021-04-12 | week 1 1: 3
|  |  | Steve | Classes UI 1.2. Roster Details | 2021-04-08 | week 1 1: 5
|  |  | Steve | Classes UI 1.2. Roster Details | 2021-04-09 | bar: week 1 1
|  |  | Steve | Classes UI 1.2. Roster Details | 2021-04-10 | bar: week 1 1
|  |  | Steve | Classes UI 1.2. Roster Details | 2021-04-12 | bar: week 1 1
|  |  | Joe | Classes UI 1.2 Class Details | 2021-04-09 | week 1 1: 2
|  |  | Joe | Classes UI 1.2 Class Details | 2021-04-10 | week 1 1: 0.5
|  |  | Joe | Classes UI 1.2 Class Details | 2021-04-11 | week 1 1: 1.5
|  |  | Joe | Classes UI 1.2 Class Details | 2021-04-12 | week 1 1: 0.5
|  |  | Joe | Classes UI 1.2 Class Details | 2021-04-13 | bar: week 1 1
|  |  | Michael | Classes UI 1.3 Completed Classes | 2021-04-14 | week 1 1: 6
|  |  | Michael | Integrate database and UIs | 2021-04-19 | week 1 1: 2

## Sprint 6
Teacher's Pet
Sprint #6 Tracking
Sprint #: |  | 6
Start date: |  | 2021-04-13
Total Team Members: |  | 4
Units allocated: |  | 41
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Tuesday | 2 Wednesday | 3 Thursday | 4 Friday | 5 Saturday | 6 Sunday | 7 Monday | 8 Tuesday | 9 Wednesday | 10 Thursday | 11 Friday | 12 Saturday | 13 Sunday | 14 Monday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | Actual
|  | build | Teacher course complete/current/future screens | Michael | 4 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  | build | Student course detail screens | Joe | 6 | 0 | 0 | 0.5 | 1 | 0 | 0.5 | 1 | 1 | 0.5 | 0 | 0 | 0.5 | 1 | 2 | 8
|  | build | Dynamic data in templates | Stephen | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2
|  | build | Teacher course detail screens | TBD | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | build | Integrate database with Admin Course screens | Sally | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
|  | build | Integrate teacher/courses screen w/ database | Sally | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
|  | build | Integrate students screen w/ database | Sally | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | build | Roster screen - complete and integrate with database | Sally | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
|  | build | Make students1_1,1_2,1_3 into a single template | Sally | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
|  | build | make teachers1_1,1_2,1_3 into a single template | sally | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | build | make admin1_1,1_2,1_3 into a single template | sally | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | build | Simplify terms current/future/compl - filter by daterange instead of current/future/compl field | Sally | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | build | Move sqlite3 database to MySQL db on CPanel | Sally | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | build | Terms lookup screen | Sally | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining units (actual) | 64 | 64 | 58 | 57.5 | 56.5 | 56.5 | 56 | 54 | 53 | 52.5 | 52.5 | 52.5 | 41 | 35 | 32
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 41
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Michael | Teacher course complete/current/future screens | 2021-04-14 | week 1 1: 6
|  |  | Michael | Integrate database and UIs as they are created | 2021-04-19 | week 1 1: 2
|  |  | Joe | Student course detail screens | 2021-04-15 | week 1 1: 0.5
|  |  | Joe | Student course detail screens | 2021-04-16 | bar: week 1 1
|  |  | Joe | Student course detail screens | 2021-04-18 | week 1 1: 0.5
|  |  | Joe | Student course detail screens | 2021-04-19 | bar: week 1 1
|  |  | Joe | Student course detail screens | 2021-04-20 | bar: week 1 1
|  |  | Joe | Student course detail screens | 2021-04-21 | week 1 1: 0.5
|  |  | Steve | Dynamic data in templates | 2021-04-19 | bar: week 1 1
|  |  | Sally | Integrate database with Admin Course screens | 2021-04-24 | week 1 1: 2
|  |  | Sally | Integrate teacher/courses screen w/ database | 2021-04-24 | week 1 1: 2
|  |  | Sally | Integrate students screen w/ database | 2021-04-24 | bar: week 1 1
|  |  | Sally | Roster screen - complete and integrate with database | 2021-04-24 | week 1 1: 2
|  |  | Sally | Make students1_1,1_2,1_3 into a single template | 2021-04-24 | week 1 1: 2
|  |  | Sally | make teachers1_1,1_2,1_3 into a single template | 2021-04-24 | bar: week 1 1
|  |  | Sally | make admin1_1,1_2,1_3 into a single template | 2021-04-24 | bar: week 1 1
|  |  | Sally | Simplify terms current/future/compl - filter by daterange instead of current/future/compl field | 2021-04-25 | week 1 1: 2
|  |  | Sally | Terms lookup screen | 2021-04-25 | week 1 1: 2
|  |  | Sally | Move sqlite3 database to MySQL db on CPanel | 2021-04-26 | bar: week 1 1
|  |  | Michael | Move sqlite3 database to MySQL db on CPanel | 4/272021 | bar: week 1 1
|  |  | Joe | Student course detail screens | 2021-04-24 | week 1 1: 0.5
|  |  | Joe | Student course detail screens | 2021-04-25 | bar: week 1 1
|  |  | Joe | Student course detail screens | 2021-04-26 | week 1 1: 2
|  |  | Joe | Student course detail screens | 2021-04-27 | week 1 1: 2
|  |  | Steve | Dynamic data in templates | 2021-04-25 | bar: week 1 1

## Sprint 7
Teacher's Pet
Sprint #7 Tracking
Sprint #: |  | 7
Start date: |  | 2021-04-27
Total Team Members: |  | 4
Units allocated: |  | 76
[6 empty] | week 1 | [6 empty] | week 2 | [6 empty] | week 3
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[6 empty] | 1 Tuesday | 2 Wednesday | 3 Thursday | 4 Friday | 5 Saturday | 6 Sunday | 7 Monday | 8 Tuesday | 9 Wednesday | 10 Thursday | 11 Friday | 12 Saturday | 13 Sunday | 14 Monday | 15 Tuesday | 16 Wednesday | 17 Thursday | 18 Friday | 19 Saturday | 20 Sunday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16 | Actual
|  | build | Screen - student/course detail | Joe | 8 | 0 | 0 | 0 | 0 | 2 | 0.5 | 2 | 0.5 | 2 | 0 | 0 | 0 | 0 | 4 | 0.5 | 0 | 0 | 0 | 1 | 0 | 12.5
|  | build | Screen -grades | Michael | 8 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5
|  | build | Screen - course assignments | Michael | 8 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.5 | 0.5 | 0 | 0 | 4
|  | design | Design a test plan | Steve | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | Build | Course roster template - do not show grades unless user is the class teacher or in the admin group | Steve | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2
|  | build | Term lookup screens - Fix delete function, update function templates - error messages, make them prettier | TBD | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | build | Function for all screens - search bar and filter | TBD | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  | build | Permissions - use groups to control access to screens (only admins see admin stuff, only teachers see teacher stuff, etc) | Sally | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  | build | Permissions - Limit menu items based on permissions group | Sally | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | build | Screen - grades - fix query to point to a particular student's assignments/grades for a scheduled course | Sally | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 5
|  | build | Admin dashboard | Sally | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | build | User maintenance screens | Sally | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 6
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining units (actual) | 64 | 64 | 64 | 64 | 64 | 59 | 58.5 | 52.5 | 52 | 48 | 48 | 48 | 44 | 37 | 30 | 29.5 | 28 | 23.5 | 23 | 18 | 18
|  |  |  | Remaining units (ideal) |  | 60.8 | 57.6 | 54.4 | 51.2 | 48 | 44.8 | 41.6 | 38.4 | 35.2 | 32 | 28.8 | 25.6 | 22.4 | 19.2 | 16 | 12.8 | 9.6 | 6.4 | 3.2 | -2.0428e-14
[11 empty] | 0 | 76
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Sally | Permissions - use groups to control access to screens (only admins see admin stuff, only teachers see teacher stuff, etc) | 2021-05-05 | week 1 1: 2
|  |  | Michael | Screen -grades | 2021-05-01 | week 1 1: 1.5
|  |  | Michael | Screen - course assignments | 2021-05-01 | week 1 1: 1.5
|  |  | Joe | Screen - student/course detail | 2021-05-01 | week 1 1: 2
|  |  | Joe | Screen - student/course detail | 2021-05-02 | week 1 1: 0.5
|  |  | Joe | Screen - student/course detail | 2021-05-03 | week 1 1: 2
|  |  | Joe | Screen - student/course detail | 2021-05-04 | week 1 1: 0.5
|  |  | Joe | Screen - student/course detail | 2021-05-05 | week 1 1: 2
|  |  | Steve | Function for all screens - search bar and filter | 2021-05-03 | week 1 1: 2
|  |  | Steve | Design a test plan | 2021-05-03 | bar: week 1 1
|  |  | Steve | Course roster template - do not show grades unless user is the class teacher or in the admin group | 2021-05-03 | bar: week 1 1
|  |  | Sally | Screen - grades - fix query to point to a particular student's assignments/grades for a scheduled course | 2021-05-09 | week 1 1: 4
|  |  | Sally | Permissions - Limit menu items based on permissions group | 2021-05-09 | bar: week 1 1
|  |  | Sally | Permissions - use groups to control access to screens (only admins see admin stuff, only teachers see teacher stuff, etc) | 2021-05-09 | week 1 1: 2
|  |  | Steve | Function for all screens - search bar and filter | 2021-05-10 | week 1 1: 3
|  |  | Sally | User maintenance screens | 2021-05-13 | week 1 1: 2
|  |  | Sally | User maintenance screens | 2021-05-15 | week 1 1: 4
|  |  | Michael | Screen -grades | 2021-05-08 | week 1 1: 4
|  |  | Joe | Screen - student/course detail | 2021-05-10 | week 1 1: 4
|  |  | Joe | Screen - student/course detail | 2021-05-11 | week 1 1: 0.5
|  |  | Joe | Screen - course assignments | 2021-05-12 | week 1 1: 1.5
|  |  | Joe | Screen - course assignments | 2021-05-13 | week 1 1: 0.5
|  |  | Joe | Screen - course assignments | 2021-05-14 | week 1 1: 0.5
|  |  | Joe | Screen - student/course detail | 2021-05-15 | bar: week 1 1
|  |  | Steve | Course roster template - do not show grades unless user is the class teacher or in the admin group | 2021-05-13 | bar: week 1 1
|  |  | Steve | Screen - grades - fix query to point to a particular student's assignments/grades for a scheduled course | 2021-05-13 | bar: week 1 1

## Sprint 8
Teacher's Pet
Sprint #8 Tracking
Sprint #: |  | 8
Start date: |  | 2021-05-15
Total Team Members: |  | 4
Units allocated: |  | 71
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Saturday | 2 Sunday | 3 Monday | 4 Tuesday | 5 Wednesday | 6 Thursday | 7 Friday | 8 Saturday | 9 Sunday | 10 Monday | 11 Tuesday | 12 Wednesday | 13 Thursday | 14 Friday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-05-15 | 2021-05-16 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-20 | 2021-05-21 | 2021-05-22 | 2021-05-23 | 2021-05-24 | 2021-05-25 | 2021-05-26 | 2021-05-27 | 2021-05-28 | Actual
|  | Build | Course assignment create | Michael | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 2
|  | Build | course assignment delete | Michael | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5
|  | Build | Course assignment update | Michael | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5
|  | Build | course assignments list | Michael | 8 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 1.5 | 0 | 1 | 0 | 0 | 0 | 10.5
|  | Build | Course schedule create |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2
|  | Build | Course schedule delete |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2
|  | Build | Course schedule update |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1.5
|  | Build | Course student grade |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Build | Courses create |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3
|  | Build | Courses delete |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | Build | Courses update |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
|  | Build | Courses list |  | 2 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 1 | 8
|  | Build | Student assignment + submission + grade |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Build | Student submission |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Build | Research automated testing in Django | Sally | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
|  | Build | Fill database with sample data | Sally | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  | Build | Add date graded to StudentSubmissions table and screens | Sally | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining units (actual) | 64 | 64 | 64 | 64 | 63 | 61 | 55 | 43 | 40 | 36.5 | 35 | 32.5 | 30.5 | 25.5 | 19
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 71
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Sally | Fill database with sample data | 2021-05-21 | week 1 1: 2
|  |  | Sally | Fill database with sample data | 2021-05-21 | week 1 1: 6
|  |  | Sally | Add date graded to StudentSubmissions table and screens | 2021-05-20 | bar: week 1 1
|  |  | Joe | Courses list | 2021-05-18 | bar: week 1 1
|  |  | Joe | Courses list | 2021-05-19 | week 1 1: 2
|  |  | Joe | Courses list | 2021-05-20 | bar: week 1 1
|  |  | Joe | course assignments list | 2021-05-21 | week 1 1: 2
|  |  | Joe | course assignments list | 2021-05-23 | week 1 1: 1.5
|  |  | Steve | Course schedule create | 2021-05-22 | bar: week 1 1
|  |  | Steve | Course schedule delete | 2021-05-22 | bar: week 1 1
|  |  | Steve | Course schedule update | 2021-05-22 | bar: week 1 1
|  |  | Michael | course assignments list | 2021-05-20 | week 1 1: 4
|  |  | Michael | course assignments list | 2021-05-21 | week 1 1: 2
|  |  | Michael | Course assignment create | 2021-05-23 | bar: week 1 1
|  |  | Michael | Course assignment update | 2021-05-23 | week 1 1: 0.5
|  |  | Michael | course assignment delete | 2021-05-23 | week 1 1: 0.5
|  |  | Sally | Course assignment create | 2021-05-27 | bar: week 1 1
|  |  | Sally | Course schedule create | 2021-05-28 | bar: week 1 1
|  |  | Sally | Course schedule update | 2021-05-28 | week 1 1: 0.5
|  |  | Sally | Course schedule delete | 2021-05-28 | bar: week 1 1
|  |  | Sally | Student submission | 2021-05-29 | week 1 1: 2
|  |  | Sally | Research automated testing in Django | 2021-05-28 | week 1 1: 2
|  |  | Michael | Student submission | 2021-05-30 | week 1 1: 2
|  |  | Steve | Courses list | 2021-05-24 | bar: week 1 1
|  |  | Steve | course assignments list | 2021-05-25 | bar: week 1 1
|  |  | Steve | Course student grade | 2021-05-27 | bar: week 1 1
|  |  | Steve | Courses list | 2021-05-28 | bar: week 1 1
|  |  | Joe | Courses list | 2021-05-24 | week 1 1: 0.5
|  |  | Joe | Courses list | 2021-05-25 | week 1 1: 1.5
|  |  | Joe | Courses update | 2021-05-26 | week 1 1: 2
|  |  | Joe | Courses create | 2021-05-27 | week 1 1: 3
|  |  | Joe | Courses delete | 2021-05-28 | bar: week 1 1

## Sprint 9
Teacher's Pet
Sprint #9 Tracking
Sprint #: |  | 9
Start date: |  | 2021-05-30
Total Team Members: |  | 4
Units allocated: |  | 97
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Sunday | 2 Monday | 3 Tuesday | 4 Wednesday | 5 Thursday | 6 Friday | 7 Saturday | 8 Sunday | 9 Monday | 10 Tuesday | 11 Wednesday | 12 Thursday | 13 Friday | 14 Saturday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-05-30 | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-05 | 2021-06-06 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-12 | Actual
| Appearance | Build | Teaching and My Courses need headers to indicate whether it's teacher or student view | Steve | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Appearance | Build | Add the fun graphics back to screens | Steve | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Appearance | Build | Make all the screens' appearance consistent | Steve | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Appearance | Build | Add student count to the student/teachers screen | Sally | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Course assignment | Build | Course assignment create/update/delete | Michael | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Course grades | Build | Course student grade |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Course grades | Build | Function - course grade calculated based on assignments |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Course schedule | Build | Course schedule update/create/delete | Sally | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Student assignment/submission | build | Student assignment + submission + grade | Michael | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Student assignment/submission | Build | Student submission create/update/delete | Michael | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| Student assignment/submission | Build | Student assignments screen - grade/submit buttons based on teacher vs student |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Student assignment/submission | Build | Student assignment screen - get rid of delete/edit/create buttons |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | Design | Design User Acceptance Test plan | Joe | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | Build | Test all screens and functions based on UAT plan | Joe | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining units (actual) | 64 | 63 | 63 | 63 | 60 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 97
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours
|  |  | Sally | Add student count to the student/teachers screen | 2021-06-02 | week 1 1: 3
|  |  | Sally | Course schedule update/create/delete | 2021-06-03 | week 1 1: 2
|  |  | Sally | Student submission create/update/delete | 2021-05-30 | bar: week 1 1
|  |  | Sally | Student assignment + submission + grade | 2021-05-03 | week 1 1: 2

## Lookup values
Team members
Joe
Michael
Sally
Steve

## Sprint template
Teacher's Pet
Sprint #0 Tracking
Sprint #: |  | 0
Start date: |  | 2021-03-07
Total Team Members: |  | 4
Units allocated: |  | 0
[6 empty] | week 1 | [6 empty] | week 2
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | 1 Sunday | 2 Monday | 3 Tuesday | 4 Wednesday | 5 Thursday | 6 Friday | 7 Saturday | 8 Sunday | 9 Monday | 10 Tuesday | 11 Wednesday | 12 Thursday | 13 Friday | 14 Saturday
Task ID | Story | Type of task | Description | Responsibility | Initial estimate | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | Actual
30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Remaining units (actual) | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64
|  |  |  | Remaining units (ideal) |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[11 empty] | 0 | 0
[11 empty] | 10 | 0
Time Entry (hours)
|  |  | Team member | Task | Date | week 1 1: Hours

## Product backlog
Project Name
| Organizations | Orange Team
| Project | Teacher's Pet Application
| Product Owner | Joe
| Scrum Master | Michael
| Development Team | Sally and Steve
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | User Interface | As a user of the Teacher's Pet app, I will find the UI intuitive and pleasing to use. | Minimal training and documentation required to use the application, users enjoy using the application | Must have
2 | Data Storage | As a user of the Teacher's pet app, I will be able to store and retrieve data. | All data elements are represented in the database | Must have
3 | Security | As a user of the Teacher's Pet app, I will be confident that data is secure and protected from breaches. | The application will use passwords for when the teacher uses the application and the student will be using passwords as well. | Must have
4 | Student Personal Info | As a student, I am able to manage my personal information | Student can see grades and class schedules, add/update personal information: address, phone number, emergency contact, allergies, medications | Must have
5 | Academic Performance Tracker | As a teacher, I am able to manage students’ academic performance | Teacher can input and track individual student grades for homework assignments and tests and calculate GPA for classes and overall. Teacher can comment on assignments for students to get feedback. | Must have
6 | Teacher Stats | As a school administrator, I am able to keep track of teacher qualifications | Input and track teachers' degrees and certifications | Must have
7 | Schedule Maintenance | As a school administrator, I am able to set and monitor both student and teacher schedules. | Input and track teacher' schedules, input and track students' schedules, calculate classroom allocations | Must have
8 | Account creation | As a school administrator, I am able to create accounts and assign account permissions | Only admin account can create other accounts. Accounts created have proper permissions and access | Must have
100 | Admin account add | Administrators can add accounts |  | must have
101 | Admin account delete | Administrators can delete accounts |  | must have
102 | Admin account update | Administrators can update accounts |  | must have
103 | Admin account view | Administrators can view accounts |  | must have
104 | Admin password reset | Administrators can request password resets for all users |  | must have
105 | Student info modify | Students can modify their personal information |  | must have
106 | Student info view | Students can view their personal information |  | must have
107 | Teacher info modify | Teachers can modify their personal information |  | must have
108 | Teacher info view | Teachers can view their personal information |  | must have
109 | Teacher qualifications add | Teachers can add their qualifications |  | must have
110 | Teacher qualifications delete | Teachers can delete their qualifications |  | must have
111 | Teacher qualifications modify | Teachers can modify their qualifications |  | must have
112 | Teacher qualifications view | Teachers can view their qualifications |  | must have
113 | Admin qualifications add | Administrators can add teacher qualifications |  | should have
114 | Admin qualifications modify | Administrators can modify teacher qualifications |  | should have
115 | Admin qualificiations delete | Administrators can delete teacher qualifications |  | should have
116 | Admin qualifications view | Administrators can view teacher qualifications |  | must have
200 | Admin class add | Administrators can add classes |  | must have
201 | Admin class update | Administrators can update classes |  | must have
202 | Admin class view | Administrators can view classes |  | must have
203 | Teacher class view | Teachers can view classes |  | should have
204 | Admin term add | Administrators can add terms |  | must have
205 | Admin term modify | Administrators can modify terms |  | must have
206 | Admin term view | Administrators can view terms |  | must have
207 | Teacher term view | Teachers can view terms |  | should have
208 | Admin schedule classes | Administrators can schedule classes |  | must have
209 | Admin view scheduled classes | Administrators can view scheduled classes |  | must have
210 | Admin Assign Teacher | Administrators can assign teachers to scheduled classes |  | must have
211 | Admin enroll students | Administrators can enroll students in scheduled classes |  | must have
212 | Admin view scheduled class enrollments | Administrators can see the students enrolled in a scheduled class |  | must have
213 | Admin withdraw students | Administrators can withdraw students from scheduled classes |  | must have
217 | Students view scheduled classes | Students can view their scheduled classes |  | must have
220 | Teacher view scheduled class enrollments | Teachers can view scheduled class enrollments |  | must have
221 | Teacher add/modify class assignments | Teachers cann add and modify assignments for scheduled classes |  | nice to have
222 | Student upload submissions | Students can upload submissions for assignments |  | nice to have
223 | Teacher view scheduled classes | Teacher can upload learning materials for a scheduled class |  | nice to have
301 | Student grades view | Students can view their grades for scheduled classes |  | must have
302 | Teacher grades modify | Teachers can modify students' grades in scheduled classes |  | must have
303 | Teacher grades view | Teachers can view their students' grades for scheduled classes |  | must have
400 | Login system | all users can log into the system using their username and password. System routes the user to the portal after successful login. |  | must have
401 | Main Portal | A portal page is displayed after successful login. Feature availability is based on user type. |  | must have